## Sheet1
Phase | Task | Owner | Notes
Pre-requisite | Ensure Metrics Server is installed and operational | DevOps | Run `kubectl top pods` to verify metrics availability
Pre-requisite | Verify Cluster Autoscaler is enabled with correct ASG tags | Infra | Ensure ASGs have k8s.io/cluster-autoscaler/enabled tag
Pre-requisite | Identify namespaces and workloads to apply HPA | Platform | Start with dev/intg/accp namespaces
Pre-requisite | Backup current Deployment YAMLs | DevOps | Export YAMLs using `kubectl get deploy -o yaml`
Configuration | Add CPU & memory requests/limits to containers in Deployments | DevOps | Mandatory for HPA to work with CPU/Memory
Configuration | Use conservative resource values as starting point | DevOps | Example: 200m CPU, 256Mi memory as requests
Configuration | Ensure updates are rolled out without pod disruption | DevOps | Use `kubectl rollout status` to monitor updates
HPA Deployment | Create HPA manifests using autoscaling/v2 API | DevOps | HPA kind: HorizontalPodAutoscaler
HPA Deployment | Configure CPU and memory average utilization thresholds | DevOps | Example: CPU 60%, Memory 70%
HPA Deployment | Set minReplicas to 1 and maxReplicas to 2 | DevOps | Prevent over-scaling and unnecessary costs
Monitoring & Validation | Run `kubectl get hpa` and `describe hpa` for status check | DevOps | Check current vs desired replicas
Monitoring & Validation | Watch scaling events via `kubectl get events` | DevOps | Capture messages like 'Scaled up/down replica set'
Monitoring & Validation | Monitor `kubectl top pods` for live metrics | DevOps | Validate usage under load scenarios
Monitoring & Validation | Use CloudWatch, Prometheus or Grafana for visual tracking | DevOps | Cloud-native observability recommended
Optimization | Analyze scale behavior post-deployment | DevOps | Ensure scaling doesn't cause instability
Optimization | Use tools like Goldilocks or VPA for tuning requests/limits | DevOps | Review namespace-wide suggestions
Optimization | Tweak scale-in/out policies if needed | DevOps | Modify scale policies (e.g. stabilizationWindowSeconds)
Optimization | Expand HPA to other namespaces and workloads | DevOps | Apply proven pattern across environments